## Dashboard
PATIENT READMISSION PROJECT — 16-DAY EXECUTION DASHBOARD
[7 empty] | Status | Count
Project start | 2026-08-03 | Project end | 2026-08-18 |  | Team size | 4 | Backlog | 42
[7 empty] | In Progress | 4
|  | Workload by owner |  |  |  |  | Review | 0
Total tasks | 57 | Owner | Tasks | Done |  |  | Done | 11
Done | 11 | Member A - Data | 14 | 7 |  |  | Blocked | 0
In Progress | 4 | Member B - ML | 14 | 0
Review | 0 | Member C - Backend | 13 | 1
Blocked | 0 | Member D - MLOps/Docs | 16 | 3
Completion | 19.3%
Phase progress
How to use |  | Phase | Total | Done | Progress
1. Replace Member A–D with real names in the Task Board owner column. |  | Phase 1 | 8 | 7 | 87.5%
2. Update Status daily: Backlog → In Progress → Review → Done. |  | Phase 2 | 12 | 4 | 33.33%
3. Add pull request or commit links for contribution evidence. |  | Phase 3 | 11 | 0 | 0%
4. Do not add features after Day 12 unless fixing a critical defect. |  | Phase 4 | 6 | 0 | 0%
4. Use Phase Guide for phase gates and Task Details for acceptance criteria. |  | Phase 5 | 7 | 0 | 0%
5. Do not mark Done without PR/commit/test evidence and required review. |  | Phase 6 | 7 | 0 | 0%
6. Freeze feature development after Day 12; only critical fixes afterward. |  | Phase 7 | 6 | 0 | 0%

## Task Board
Task ID | Phase | Workstream | Task | Owner | Priority | Status | Start Date | Due Date | Deliverable / Definition of Done | Dependency | PR / Commit Link | Notes | Reviewer | Output Path / Artifact | Acceptance Summary | Evidence Required
PM-01 | Phase 1 | Project | Create repository, branches, .gitignore and base folders | Member D - MLOps/Docs | Critical | Done | 2026-08-03 | 2026-08-03 | Repository structure committed | None |  |  | Member A | Repository root, .gitignore, remote branches and collaborator access | Required branches exist remotely; Base structure and .gitignore are committed; All four members can clone and push to assigned branches; No raw data, secrets, .env, .venv or large model artifacts are tracked | Repository URL, branch list and commit/PR link
PM-02 | Phase 1 | Project | Create task board and assign owners | Member D - MLOps/Docs | High | Done | 2026-08-03 | 2026-08-03 | All tasks have owner and deadline | PM-01 |  |  | Member A | GitHub Project or synchronized tracker workbook | Every task has a unique ID, owner and deadline; Dependencies and deliverables are present; Status workflow is documented; Evidence fields exist and no duplicate task IDs remain | Board/workbook link or screenshot
DOC-01 | Phase 1 | Documentation | Draft problem statement, users, scope and success metrics | Member D - MLOps/Docs | High | Done | 2026-08-03 | 2026-08-04 | Problem definition document | None |  |  | Members A, B and C | docs/PROBLEM_DEFINITION.md | Business context and users are explicit; Prediction point prevents future-data leakage; Target mapping is stated and marked for data-dictionary confirmation; Functional/non-functional requirements and success metrics are included | PR/commit link and review comments
DATA-01 | Phase 1 | Data | Download and version Diabetes 130-US Hospitals dataset | Member A - Data | Critical | Done | 2026-08-03 | 2026-08-03 | Raw dataset plus checksum/metadata | None |  |  | Member B | data/metadata/dataset_metadata.json and local data/raw files | Files open successfully and checksum is recorded; Source/version metadata is complete; Raw files are immutable and ignored by Git; No patient-level raw data is committed | Metadata file and checksum command/output
DATA-02 | Phase 1 | Data | Inspect schema, missing values, duplicates and class balance | Member A - Data | Critical | Done | 2026-08-03 | 2026-08-04 | Initial EDA report | DATA-01 |  |  | Member B | notebooks/01_data_understanding.ipynb and reports/initial_eda.md | Schema table is complete; Missing values including special tokens are counted; Duplicate count and target distribution are reported; Notebook/report is reproducible and does not modify raw data | Notebook/report PR and rendered tables/plots
DATA-03 | Phase 1 | Data | Define 30-day readmission target and leakage exclusions | Member A - Data | Critical | Done | 2026-08-04 | 2026-08-04 | Target mapping and leakage checklist | DATA-02 |  |  | Members B and C | docs/TARGET_AND_LEAKAGE.md | Target mapping is verified against actual values; Prediction point is explicit; Each excluded field has a reason; Target and future information cannot enter features | PR link and leakage checklist
ML-01 | Phase 1 | ML | Define evaluation metrics and MLflow experiment structure | Member B - ML | High | In Progress | 2026-08-03 | 2026-08-04 | Metric specification and experiment name | None |  |  | Member C | docs/ML_EVALUATION_SPEC.md and configs/mlflow.yaml | A primary selection metric is named; Calibration and operational metrics are defined; MLflow convention is reproducible; Required versions/tags/artifacts are listed | PR link and specification review
API-01 | Phase 1 | Backend | Create FastAPI skeleton with /health, /ready and /api/v1/predict | Member C - Backend | High | Done | 2026-08-03 | 2026-08-04 | Running API skeleton with mock response | PM-01 |  |  | Member D | src/api, src/config, tests/integration/test_api.py | Application imports and starts; /docs and /openapi.json load; /health returns 200; /ready reports mock/not-loaded state | PR/commit, test output and Swagger screenshot
DATA-04 | Phase 2 | Data | Implement data ingestion script | Member A - Data | Critical | Done | 2026-08-05 | 2026-08-05 | Reproducible raw-to-interim script | DATA-01 |  |  | Member B | src/data/ingestion.py and data/metadata/ingestion_manifest.json | python -m src.data.ingestion runs successfully; Same input produces the same checksum/version metadata; Missing/invalid files fail clearly; Raw data is not overwritten | Command log, manifest and PR
DATA-05 | Phase 2 | Data | Implement schema and data quality validation | Member A - Data | Critical | Done | 2026-08-05 | 2026-08-06 | Versioned validation report, data dictionary and fail-safe handling | DATA-04 |  |  | Member B | src/data/validation.py, configs/data_quality.yaml, reports/validation_report.json, docs/DATA_DICTIONARY.md | Required columns/types/labels are checked; Negative and out-of-range values are detected; Missing and duplicate rules are configuration-backed; Failure stops the pipeline and does not overwrite prior valid output | Passing/failing validation samples, report and PR
DATA-06 | Phase 2 | Data | Implement leakage-safe train/validation/test split | Member A - Data | Critical | Done | 2026-08-06 | 2026-08-06 | Saved split manifest | DATA-03 |  |  | Member B | src/data/splitting.py and data/splits/split_manifest.json | Splits do not overlap; The same patient does not cross splits when patient-aware splitting is used; Target is absent from feature columns; Seed and ratios are recorded | Split manifest, overlap test and PR
DATA-07 | Phase 2 | Data | Build preprocessing with imputation and encoding | Member A - Data | Critical | Done | 2026-08-06 | 2026-08-07 | Serializable preprocessing pipeline | DATA-05, DATA-06 |  |  | Member B | src/features/preprocessing.py and preprocessor metadata/artifact reference | Preprocessor fits only on training data; Validation/test use transform only; Unknown categories do not crash inference; Feature order/version is recorded | Unit tests, artifact checksum/reference and PR
ML-02 | Phase 2 | ML | Train Dummy Classifier baseline | Member B - ML | Low | Backlog | 2026-08-05 | 2026-08-05 | Baseline metrics in MLflow | DATA-06 |  |  | Member C | src/models/train_dummy.py and MLflow run | Run uses the versioned split; Strategy and random seed are logged; Primary/secondary metrics are stored; No test-set decision is made | MLflow run URL/ID and PR
ML-03 | Phase 2 | ML | Train Logistic Regression baseline | Member B - ML | Critical | Backlog | 2026-08-05 | 2026-08-06 | Tracked baseline run with artifacts | DATA-07 |  |  | Member C | src/models/train_logistic.py, configs/models/logistic.yaml and MLflow run | Shared DATA-07 preprocessor is used; Run is reproducible from config; Metrics and confusion matrix are logged; Model and preprocessing versions are traceable | MLflow run, config and PR
ML-04 | Phase 2 | ML | Train class-balanced Logistic Regression | Member B - ML | High | Backlog | 2026-08-06 | 2026-08-07 | Imbalance comparison table | ML-03 |  |  | Member C | reports/logistic_imbalance_comparison.md and MLflow run | Only class weighting changes between comparison runs; AUPRC, precision, recall and F1 are compared; Trade-off is explained; Test set remains untouched | Comparison table, MLflow run and PR
API-02 | Phase 2 | Backend | Create request/response Pydantic schemas | Member C - Backend | Critical | In Progress | 2026-08-05 | 2026-08-06 | Stable API contract and examples | API-01, DATA-03 |  | Draft after DATA-03; finalize against DATA-05/DATA-07 and review with Members A/B. | Members A and B | src/api/schemas.py, tests/unit/test_schemas.py, docs/api/API_CONTRACT.md | Fields match approved target/leakage policy; Types and constraints are explicit; Swagger examples render; Target/leakage fields are absent | PR, schema tests and Swagger screenshot
API-03 | Phase 2 | Backend | Implement validation and error handling | Member C - Backend | High | In Progress | 2026-08-06 | 2026-08-07 | 422/500 responses tested | API-02 |  |  | Member D | src/api/exception_handlers.py and tests/integration/test_api_errors.py | Invalid inputs return structured 422 responses; Internal failures return safe 500/503 responses; No stack trace or patient payload is exposed; Swagger documents error responses | PR and pytest output
API-04 | Phase 2 | Backend | Create API Dockerfile | Member C - Backend | Critical | In Progress | 2026-08-05 | 2026-08-07 | API image builds and container health check passes | API-01 |  |  | Member D | Dockerfile and .dockerignore | docker build succeeds; Container starts and /health returns 200; /docs is reachable; Runtime uses Python 3.11 | Build log, image tag and curl output
OPS-01 | Phase 2 | MLOps | Create Docker Compose skeleton | Member D - MLOps/Docs | Critical | Backlog | 2026-08-05 | 2026-08-07 | Docker Compose starts API service successfully | API-04 |  |  | Member C | docker-compose.yml and .env.example | docker compose config passes; docker compose up --build starts a healthy API; /health and /docs work from host; No secret is hardcoded | Compose config/output, health screenshot and PR
OPS-02 | Phase 2 | MLOps | Add MLflow service to Docker Compose | Member D - MLOps/Docs | High | Backlog | 2026-08-06 | 2026-08-07 | MLflow UI and persistent volume | ML-01 |  |  | Member A | docker-compose.yml, volume definitions and docs/MLFLOW_SETUP.md | MLflow UI is reachable; Runs persist after container restart; Training can log to the configured tracking URI; mlruns and credentials are not committed | MLflow screenshot, persistence test and PR
DATA-08 | Phase 3 | Data | Create feature set V1 from validated raw features | Member A - Data | High | Backlog | 2026-08-08 | 2026-08-08 | Feature manifest V1 | DATA-07 |  |  | Member B | configs/features/feature_set_v1.yaml and docs/features/FEATURE_SET_V1.md | Manifest has version, ordered features and types; Target/identifiers/leakage are absent; Preprocessor can consume the manifest; Missing or extra fields are testable | Manifest, unit test and PR
DATA-09 | Phase 3 | Data | Create and document limited feature set V2 | Member A - Data | Medium | Backlog | 2026-08-08 | 2026-08-09 | Feature manifest V2 and rationale | DATA-08 |  |  | Members B and C | configs/features/feature_set_v2.yaml and docs/features/FEATURE_SET_V2.md | V2 purpose and reduction rationale are explicit; V2 remains leakage-safe and prediction-time available; Manifest is versioned and loadable; Members B and C understand API/model implications | Manifest/rationale PR
DATA-10 | Phase 3 | Data | Run V1 vs V2 feature ablation support | Member A - Data | Medium | Backlog | 2026-08-09 | 2026-08-10 | Ablation dataset outputs | DATA-09 |  |  | Member B | reports/feature_ablation_inputs.md and versioned feature/preprocessor references | Only the feature set changes in the comparison; Same split and random seed are used; No train/validation/test leakage occurs; Inputs can be reproduced from committed code/configs | Checksums, commands and PR
ML-05 | Phase 3 | ML | Train default XGBoost model | Member B - ML | Critical | Backlog | 2026-08-08 | 2026-08-08 | XGBoost baseline in MLflow | DATA-08 |  |  | Member C | src/models/train_xgboost.py, configs/models/xgboost_default.yaml and MLflow run | Run uses V1 and approved split; Configuration and seed are logged; Metrics are comparable to baselines; Artifact/version traceability is complete | MLflow run, config and PR
ML-06 | Phase 3 | ML | Run class imbalance experiment for XGBoost | Member B - ML | High | Backlog | 2026-08-08 | 2026-08-09 | scale_pos_weight comparison | ML-05 |  |  | Member C | reports/xgboost_imbalance_comparison.md and MLflow runs | Weight values and rationale are recorded; Runs share split/features/evaluation; AUPRC, recall, precision and F1 are compared; Recommendation is documented without using test data | MLflow comparison and report PR
ML-07 | Phase 3 | ML | Tune XGBoost with Optuna (20-40 trials) | Member B - ML | Critical | Backlog | 2026-08-09 | 2026-08-10 | Best parameters and CV results | ML-06 |  |  | Member C | src/models/tune_xgboost.py, configs/models/xgboost_optuna.yaml and reports/optuna_results.md | Search space and objective are documented; Requested trials complete or justified early stop is recorded; Best parameters/results are reproducible; Test set is untouched | Study database/summary, MLflow runs and PR
ML-08 | Phase 3 | ML | Select candidate model and export artifacts | Member B - ML | Critical | Backlog | 2026-08-10 | 2026-08-10 | Model, preprocessor and metadata package | ML-07, DATA-10 |  |  | Member C | MLflow model bundle plus docs/MODEL_HANDOFF.md and metadata.json | Selection rationale is documented; Model/preprocessor/manifest reload successfully; Checksums and versions are recorded; Reloaded predictions match original output | MLflow artifact URI, checksums, handoff doc and PR
API-05 | Phase 3 | Backend | Implement production model loading lifecycle | Member C - Backend | Critical | Backlog | 2026-08-08 | 2026-08-10 | Model loads once at startup | API-03, ML-08 |  | Scaffold with a test bundle; cannot be Done until ML-08 handoff is validated. | Member D | src/api/lifecycle.py, src/api/dependencies.py and tests/unit/test_model_loading.py | Artifacts load once at startup; Version mismatch/corruption is detected; /ready is false when loading fails and true when complete; Production mode never silently falls back to mock | PR, startup logs without secrets and test output
API-06 | Phase 3 | Backend | Integrate real prediction pipeline into API | Member C - Backend | Critical | Backlog | 2026-08-09 | 2026-08-10 | End-to-end prediction response | API-05, ML-08 |  |  | Member D | src/api/prediction_service.py, updated routes/schemas and tests/integration/test_real_prediction_api.py | Feature order is enforced; Real preprocessor and predict_proba are used; Probability is within [0,1]; Response includes correct versions and is_mock=false | End-to-end test, curl response and PR
OPS-03 | Phase 3 | MLOps | Instrument API with Prometheus metrics | Member D - MLOps/Docs | High | Backlog | 2026-08-08 | 2026-08-09 | Metrics endpoint and counters/histograms | API-01, API-03 |  | Basic HTTP metrics can start early; prediction metrics finalize after API-06. | Member C | src/api/metrics.py and monitoring/prometheus/prometheus.yml | /metrics is reachable; Counters/histograms/gauges update correctly; Prometheus target is UP; No patient identifier or unbounded label exists | Metrics samples, Prometheus target screenshot and PR
OPS-04 | Phase 3 | MLOps | Create first Grafana dashboard | Member D - MLOps/Docs | High | Backlog | 2026-08-09 | 2026-08-10 | Requests, latency, errors, risk distribution | OPS-03, API-06 |  |  | Member C | monitoring/grafana/provisioning and monitoring/grafana/dashboards/api-overview.json | Grafana connects to Prometheus; Required panels display live data; Dashboard survives restart/provisions automatically; Risk/probability view uses aggregated metrics only | Dashboard JSON, screenshot and PR
ML-09 | Phase 4 | ML | Compare uncalibrated and sigmoid calibration | Member B - ML | High | Backlog | 2026-08-11 | 2026-08-11 | Brier score and calibration curve | ML-08 |  |  | Member C | src/models/calibration.py and reports/calibration_report.md | No test leakage occurs; Brier score and calibration curve are produced; Comparison uses the same candidate model/split; Selected calibration method and version are documented | Report, plots, MLflow run and PR
ML-10 | Phase 4 | ML | Select operating threshold from validation set | Member B - ML | Critical | Backlog | 2026-08-11 | 2026-08-12 | Threshold report with recall/precision trade-off | ML-09 |  |  | Member C | src/models/threshold_selection.py and reports/threshold_report.md | Threshold comes only from validation data; Trade-off table and rationale are explicit; Capacity-based metric is reported; Threshold/version is exportable to the API bundle | Threshold report, config/metadata update and PR
DATA-11 | Phase 4 | Responsible AI | Prepare subgroup slices and fairness metrics | Member A - Data | High | Backlog | 2026-08-11 | 2026-08-12 | Group-level performance table | ML-08 |  |  | Members B and D | src/evaluation/fairness.py and reports/fairness_metrics.md | Groups and denominators are documented; Metrics use the fixed candidate model/threshold; Small-sample limitations are flagged; No patient-level data is published | Fairness table/report and PR
ML-11 | Phase 4 | Responsible AI | Generate global SHAP explanation | Member B - ML | High | Backlog | 2026-08-12 | 2026-08-12 | SHAP summary and top features | ML-08 |  |  | Members C and D | src/models/explainability.py and reports/shap_summary.md | SHAP computation is reproducible; Global plot/top features are saved; No patient-level sensitive examples are exposed; Limitations and transformed-feature mapping are documented | SHAP artifacts/report and PR
API-07 | Phase 4 | Backend | Return probability, risk band and top factors | Member C - Backend | High | Backlog | 2026-08-11 | 2026-08-12 | Explainable API response | API-06, ML-10, ML-11 |  |  | Member D | updated src/api schemas/routes/prediction service and tests | Probability uses the selected calibration/version; Risk band follows documented thresholds; Top factors contain no raw patient identifiers; Response versions are traceable | Swagger/curl examples, boundary tests and PR
DOC-02 | Phase 4 | Responsible AI | Draft Responsible AI and Model Card | Member D - MLOps/Docs | Critical | Backlog | 2026-08-11 | 2026-08-12 | RESPONSIBLE_AI.md and MODEL_CARD.md | DATA-11, ML-11 |  |  | Members A, B and C | docs/RESPONSIBLE_AI.md and docs/MODEL_CARD.md | Documents match actual artifacts/metrics; Clinical decision-support limitation is explicit; Fairness/privacy limitations are transparent; Monitoring and human review requirements are included | PR and cross-role review comments
TEST-01 | Phase 5 | Testing | Write data quality and leakage tests | Member A - Data | Critical | Backlog | 2026-08-13 | 2026-08-14 | Passing data test suite | DATA-05, DATA-06, DATA-07 |  |  | Member B | tests/data and test fixtures | Positive and negative validation cases pass; Leakage and split-overlap failures are detected; Preprocessing round-trip is tested; Tests use no raw patient dataset | pytest output, coverage and PR
TEST-02 | Phase 5 | Testing | Write model validation tests | Member B - ML | Critical | Backlog | 2026-08-13 | 2026-08-14 | Passing model test suite | ML-08, ML-10 |  |  | Member C | tests/models | Model bundle reload test passes; Predictions are finite and within bounds; Version/feature mismatches fail clearly; Metric checks use stable fixtures/tolerances | pytest output, coverage and PR
TEST-03 | Phase 5 | Testing | Write API integration tests | Member C - Backend | Critical | Backlog | 2026-08-13 | 2026-08-14 | Valid/invalid/readiness cases pass | API-05, API-06, API-07 |  |  | Member D | tests/integration | Valid prediction succeeds; Invalid inputs return structured 422; Unavailable/corrupt model returns safe status; Readiness matches lifecycle state | pytest output, coverage and PR
API-08 | Phase 5 | Backend | Complete Swagger/OpenAPI examples | Member C - Backend | Medium | Backlog | 2026-08-13 | 2026-08-14 | Documented request and response examples | API-03, API-07 |  |  | Member D | src/api schema metadata and docs/api/openapi.json (optional generated artifact) | /docs covers all endpoints and error responses; Examples match actual tests; Required/optional fields are clear; No sensitive real patient example is included | Swagger screenshot, OpenAPI diff and PR
OPS-05 | Phase 5 | MLOps | Complete Docker Compose health checks and volumes | Member D - MLOps/Docs | Critical | Backlog | 2026-08-13 | 2026-08-14 | All services healthy after one command | OPS-01, OPS-02, OPS-04, API-04 |  |  | Member C | docker-compose.yml, volume/health configuration and docs | All services become healthy from one command; Persistent MLflow/Grafana state survives restart; API waits for required dependencies; Clean stop/reset procedure is documented | Compose ps output, restart evidence and PR
OPS-06 | Phase 5 | MLOps | Create GitHub Actions CI pipeline | Member D - MLOps/Docs | Critical | Backlog | 2026-08-13 | 2026-08-14 | Lint, tests, coverage and Docker build | TEST-01, TEST-02, TEST-03, API-04 |  |  | Member A | .github/workflows/ci.yml | Workflow triggers on pull requests/pushes as agreed; Lint and all test suites pass; Coverage is reported; Docker build succeeds | Green GitHub Actions run and PR
OPS-07 | Phase 5 | MLOps | Add meaningful alert rules | Member D - MLOps/Docs | High | Backlog | 2026-08-14 | 2026-08-14 | Latency/error/model availability alerts | OPS-03, OPS-04 |  |  | Member C | monitoring/prometheus/alerts.yml and docs/MONITORING.md | Rules load without errors; Alerts cover latency, error and model availability; Threshold rationale is documented; No patient-level labels are used | promtool/rule validation output and PR
DOC-03 | Phase 6 | Documentation | Complete README setup, training, API and troubleshooting | Member D - MLOps/Docs | Critical | Backlog | 2026-08-15 | 2026-08-16 | Comprehensive README | OPS-05, API-08 |  |  | Member A | README.md | Clean setup instructions are executable; Commands match current code and ports; Dataset/artifact policies are clear; Troubleshooting covers common failures | README PR and clean-reader review
DOC-04 | Phase 6 | Documentation | Complete architecture and data flow documentation | Member D - MLOps/Docs | Critical | Backlog | 2026-08-15 | 2026-08-16 | ARCHITECTURE.md with diagrams | DATA-10, ML-08, API-07, OPS-05 |  |  | Members A, B and C | docs/ARCHITECTURE.md and docs/architecture-diagram.png | Diagram and prose match implementation; Data/model/API/monitoring handoffs are shown; Dependencies and failure behavior are explained; All four roles review their components | Architecture PR and diagram review
DOC-05 | Phase 6 | Presentation | Build presentation deck and story | Member D - MLOps/Docs | Critical | Backlog | 2026-08-15 | 2026-08-16 | 15-20 minute slide deck | DOC-02, DOC-04 |  |  | All members | presentation deck and source assets | Deck fits 15-20 minutes; Claims match final evidence; All roles have clear speaking sections; Architecture/results/Responsible AI/demo are covered | Deck file, rehearsal timing and review notes
DATA-12 | Phase 6 | Documentation | Write data and leakage section | Member A - Data | High | Backlog | 2026-08-15 | 2026-08-16 | Data section ready for README/slides | TEST-01 |  |  | Member B | docs/sections/DATA_AND_LEAKAGE.md | Text matches final pipeline/configs; Leakage safeguards are explicit; Data limitations are transparent; Figures/tables are reproducible and privacy-safe | Section PR and source figure links
ML-12 | Phase 6 | Documentation | Write model, tuning, calibration and threshold section | Member B - ML | High | Backlog | 2026-08-15 | 2026-08-16 | Model results section ready | TEST-02 |  |  | Member C | docs/sections/MODEL_RESULTS.md | Metrics match frozen MLflow/report values; Validation versus test usage is clear; Threshold/calibration rationale is included; No unsupported superiority claim is made | Section PR and MLflow/report references
API-09 | Phase 6 | Documentation | Write API, Docker and demo instructions | Member C - Backend | High | Backlog | 2026-08-15 | 2026-08-16 | Deployment and demo guide | TEST-03, API-08, OPS-05 |  |  | Member D | docs/DEMO_GUIDE.md | Commands work from a clean environment; Examples match final OpenAPI schema; Docker/Compose steps are accurate; Failure recovery and fallback are documented | Guide PR and clean-run evidence
DEMO-01 | Phase 6 | Presentation | Prepare live demo script and backup evidence | Member C - Backend | Critical | Backlog | 2026-08-16 | 2026-08-16 | Demo script, screenshots and curl examples | API-09 |  |  | Member D | docs/DEMO_SCRIPT.md and docs/demo_evidence | Live flow can be completed within allocated time; Backup evidence covers every critical step; Failure scenario is understandable; Examples use synthetic/non-sensitive data | Script, screenshots and rehearsal notes
QA-01 | Phase 7 | Quality | Run clean end-to-end pipeline and full test suite | Member A - Data | Critical | Backlog | 2026-08-17 | 2026-08-17 | Reproducible clean run evidence | DATA-07, ML-10, API-07, OPS-05, OPS-06 |  |  | Member B | reports/qa/clean_end_to_end_run.md | Clean run completes without hidden local state; All required tests pass; Versions/checksums are recorded; Any approved manual step is documented | Clean-run log and checklist
QA-02 | Phase 7 | Quality | Validate final holdout metrics and model artifacts | Member B - ML | Critical | Backlog | 2026-08-17 | 2026-08-17 | Final metric table and artifact checksum | QA-01, ML-08, ML-10 |  |  | Member C | reports/qa/final_holdout_metrics.md and artifact checksums | Holdout is evaluated only after decisions are frozen; Metrics match saved predictions/artifacts; Checksums verify the submitted bundle; No post-hoc retuning occurs | Final metric table, MLflow run and checksum output
QA-03 | Phase 7 | Quality | Run clean Docker Compose smoke test | Member C - Backend | Critical | Backlog | 2026-08-17 | 2026-08-17 | All endpoints and services verified | OPS-05, API-07 |  |  | Member D | reports/qa/compose_smoke_test.md | All services become healthy; Endpoints and dashboards are reachable; Real prediction and errors behave correctly; Persistent services survive restart | Compose ps, curl outputs and screenshots
QA-04 | Phase 7 | Quality | Audit documentation, commits and rubric coverage | Member D - MLOps/Docs | Critical | Backlog | 2026-08-17 | 2026-08-18 | Submission checklist completed | DOC-03, DOC-04, DOC-05, QA-01, QA-02, QA-03 |  |  | All members | docs/SUBMISSION_CHECKLIST.md | Every rubric item has evidence or an explicit limitation; Each member has traceable contributions; All files/links open; Repository security/data policy checks pass | Completed checklist and audit notes
DEMO-02 | Phase 7 | Presentation | Technical rehearsal with timed handoffs | Member D - MLOps/Docs | Critical | Backlog | 2026-08-18 | 2026-08-18 | Full rehearsal completed | DOC-05, DEMO-01, QA-03 |  |  | All members | docs/REHEARSAL_LOG.md | Full run fits the time limit; Speaker handoffs are explicit; Critical Q&A ownership is practiced; Actions are resolved before submission | Rehearsal log and timing
DEMO-03 | Phase 7 | Presentation | Failure rehearsal and backup demo verification | Member C - Backend | High | Backlog | 2026-08-18 | 2026-08-18 | Offline backup tested | DEMO-02, QA-03 |  |  | Member D | docs/BACKUP_DEMO_CHECKLIST.md and backup assets | Offline backup opens without external dependency; Failure scenario and recovery are demonstrated; Assets match the final system; No sensitive data is included | Completed checklist and backup asset test

## 16-Day Timeline
16-DAY PARALLEL EXECUTION TIMELINE
Day | Date | Phase | Primary Goal | Member A - Data | Member B - ML | Member C - Backend | Member D - MLOps/Docs
Day 1 | 2026-08-03 | Phase 1 | Kickoff and foundations | Dataset download and schema scan | Metrics and MLflow setup | FastAPI skeleton | Repo, board, architecture
Day 2 | 2026-08-04 | Phase 1 | Lock problem and schema | Target, leakage and EDA | Training skeleton | FastAPI skeleton; API contract draft | Problem statement, repository and task governance
Day 3 | 2026-08-05 | Phase 2 | Data pipeline and baseline | Ingestion and validation | Dummy + Logistic baseline | Pydantic schemas + API Dockerfile | Compose skeleton + MLflow service
Day 4 | 2026-08-06 | Phase 2 | Preprocessing and integration | Split and preprocessing | Balanced Logistic | Validation/error handling | Compose networking + MLflow persistence
Day 5 | 2026-08-07 | Phase 2 | Baseline milestone | Finalize pipeline and tests | Baseline comparison | Stable contract + API image milestone | API + MLflow Compose milestone
Day 6 | 2026-08-08 | Phase 3 | XGBoost and features | Feature V1/V2 | Default XGBoost | Model lifecycle scaffold; validate handoff | Prometheus metrics
Day 7 | 2026-08-09 | Phase 3 | Tuning and real API | Ablation support | Optuna tuning | Integrate real prediction | Grafana dashboard
Day 8 | 2026-08-10 | Phase 3 | Candidate model milestone | Finalize feature artifacts | Select/export candidate | End-to-end real prediction milestone | Monitoring milestone
Day 9 | 2026-08-11 | Phase 4 | Calibration and fairness | Fairness slices | Calibration + threshold | Risk band response | Responsible AI draft
Day 10 | 2026-08-12 | Phase 4 | Explainability milestone | Fairness table | SHAP and final threshold | Top factors response | Model Card complete
Day 11 | 2026-08-13 | Phase 5 | Testing and orchestration | Data tests | Model tests | Integration tests | Compose health checks + CI
Day 12 | 2026-08-14 | Phase 5 | System freeze | Fix data defects only | Fix model defects only | Swagger and smoke tests | Alerts and full pipeline
Day 13 | 2026-08-15 | Phase 6 | Documentation and slides | Data section | Model section | API/demo guide | README, architecture, slides
Day 14 | 2026-08-16 | Phase 6 | Demo package milestone | Review documentation | Review results | Backup demo evidence | Finalize presentation
Day 15 | 2026-08-17 | Phase 7 | Full validation | Clean data run | Final holdout validation | Clean compose smoke test | Rubric and contribution audit
Day 16 | 2026-08-18 | Phase 7 | Rehearsal and freeze | Answer data Q&A | Answer ML Q&A | Run live/failure demo | Timed rehearsal and submission check

## Roles & Rules
TEAM ROLES, WORKING RULES AND CUT-SCOPE ORDER
Owner | Primary Role | Must-Have Deliverables | Reviewer | Q&A Ownership | Replace With Name
Member A - Data | Data Lead | Ingestion, validation, preprocessing, feature engineering, data tests, fairness slices | Member B | Dataset, leakage, preprocessing
Member B - ML | ML Lead | Baselines, XGBoost, Optuna, MLflow, calibration, threshold, SHAP, model tests | Member C | Metrics, tuning, threshold, explainability
Member C - Backend | Backend Lead | FastAPI, schemas, model loading, Dockerfile, integration tests, Swagger, demo | Member D | API, Docker, serving, error handling
Member D - MLOps/Docs | MLOps & Documentation Lead | Docker Compose, Prometheus, Grafana, alerts, CI/CD, docs, slides | Member A | Architecture, monitoring, Responsible AI, CI/CD
Daily operating rules
• 15-minute start-of-day stand-up: completed, today, blocker.
• End-of-day integration checkpoint: merge stable work into develop.
• Every technical task must include a deliverable and PR/commit evidence.
• At least one teammate reviews each pull request.
• Freeze feature development after Day 12; only critical defect fixes afterward.
• Never commit raw patient data, credentials, .env files, or large model binaries.
Cut scope in this order if delayed
1. Cloud deployment
2. Random Forest
3. Per-request local SHAP
4. Advanced drift detection
5. Isotonic calibration
6. Reduce Optuna trials
7. Extra Grafana dashboards
8. Advanced feature engineering
Do not cut
Logistic Regression baseline, XGBoost, MLflow, FastAPI, Docker, Docker Compose, Prometheus, at least one Grafana dashboard, tests, GitHub Actions, Responsible AI, README and architecture documentation.
Branch / work-area ownership
Member A - Data | feature/data-pipeline | Data ingestion, validation, splitting, preprocessing, feature sets and data tests
Member B - ML | feature/model-training | Baselines, XGBoost, tuning, calibration, threshold, SHAP and model tests
Member C - Backend | feature/api | FastAPI, schemas, model lifecycle, prediction service, Dockerfile, API tests and demo
Member D - MLOps/Docs | feature/monitoring + feature/responsible-ai | Compose, MLflow service, Prometheus, Grafana, CI, alerts, project/Responsible AI documentation and slides
Synchronization rule
Excel controls task IDs, owners, status and dates. The DOCX controls phase objectives, role outcomes and phase gates. GitHub PR/commit/test evidence proves completion. A task is not Done when any one of these three sources conflicts.

## Phase Guide
SYNCHRONIZED PHASE DEFINITIONS AND GITHUB GATES
Phase | Official Name | Dates | Objective | Role Outputs | Phase Gate (Done when) | Expected GitHub Updates
Phase 1 | Foundations, Problem Definition and Requirements | 03-Aug to 04-Aug | Chot business problem, prediction point, target, leakage rules, success metrics, repository governance and a runnable mock API skeleton. | A: dataset version, initial EDA, target and leakage checklist. B: evaluation metric specification and MLflow convention. C: FastAPI skeleton with health, readiness and mock prediction. D: repository, task board and problem definition. | All eight Phase 1 tasks are Done; target and leakage rules are approved; repository and branches work; mock API passes lint/tests; each task has evidence. | PRs from feature branches into develop; docs/PROBLEM_DEFINITION.md, docs/TARGET_AND_LEAKAGE.md, docs/ML_EVALUATION_SPEC.md, dataset metadata/EDA evidence, src/api skeleton and tracker updates.
Phase 2 | Reproducible Data Pipeline, Baselines, API Contract and Container Foundation | 05-Aug to 07-Aug | Build reusable ingestion, validation, split and preprocessing; establish baseline models, stable API schemas, tested error handling, API image and MLflow-enabled Compose environment. | A: raw-to-interim ingestion, versioned validation report, leakage-safe split and serializable preprocessor. B: Dummy, Logistic Regression and class-balanced Logistic Regression runs in MLflow. C: stable Pydantic contract, 422/500 handling and API Dockerfile. D: Docker Compose skeleton and persistent MLflow service. | Ingestion is reproducible; validation fails safely; split and preprocessor are versioned; baseline runs exist; API schemas/tests pass; API and MLflow start through Docker Compose. | src/data, src/features, baseline training code/configs, docs/DATA_DICTIONARY.md, validation/split metadata, API contract/tests, Dockerfile, .dockerignore, docker-compose.yml and MLflow setup documentation.
Phase 3 | Feature Engineering, Advanced Modeling, Real Model API and Initial Monitoring | 08-Aug to 10-Aug | Create versioned feature sets, train and tune XGBoost, export a candidate model bundle, replace the mock API with real inference, and expose initial Prometheus/Grafana observability. | A: feature set V1/V2 manifests and ablation-ready outputs. B: XGBoost baseline, imbalance experiment, Optuna study and candidate model bundle. C: startup model lifecycle and real end-to-end prediction. D: Prometheus metrics and the first Grafana dashboard. | Candidate bundle reloads successfully; API prediction matches offline output within tolerance; readiness reflects model state; Prometheus scrapes the API; Grafana displays request, latency, error and prediction views. | Feature manifests, XGBoost/tuning code and reports, model handoff metadata, lifecycle/prediction service tests, monitoring configuration and dashboard JSON. Large model binaries remain in MLflow/artifact storage.
Phase 4 | Calibration, Thresholding, Explainability and Responsible AI | 11-Aug to 12-Aug | Calibrate probabilities, select an operating threshold, assess subgroup behavior, generate SHAP evidence, expose explainable responses and document limitations/responsible use. | A: subgroup slices and fairness performance table. B: calibration comparison, threshold report and global SHAP analysis. C: probability, risk band and top-factor API response. D: Responsible AI document and Model Card. | Threshold is selected only from validation data; calibration evidence exists; subgroup results and limitations are documented; API response uses versioned threshold/risk logic; Model Card is reviewed. | Calibration/threshold/SHAP code and reports, fairness tables, updated API schemas/routes/tests, docs/RESPONSIBLE_AI.md and docs/MODEL_CARD.md.
Phase 5 | Testing, CI and Operational Hardening | 13-Aug to 14-Aug | Convert pipeline/model/API expectations into automated tests, complete Compose health behavior, add CI and alerts, and freeze feature development. | A: data quality and leakage test suite. B: model validation test suite. C: API integration tests and completed OpenAPI examples. D: Compose health checks/volumes, GitHub Actions and alert rules. | Lint, data tests, model tests, API tests and Docker build pass in CI; one command starts healthy services; alert rules are loadable; only critical defect fixes remain after Day 12. | tests/data, tests/models, tests/integration, OpenAPI examples, hardened docker-compose.yml, .github/workflows/ci.yml and Prometheus alert rules.
Phase 6 | Documentation, Presentation and Demo Packaging | 15-Aug to 16-Aug | Package the implementation into reproducible documentation, architecture/data-flow explanations, role-authored result sections, presentation story and live/backup demo instructions. | A: data and leakage write-up. B: model, tuning, calibration and threshold write-up. C: API/Docker/demo guide plus live and backup evidence. D: comprehensive README, architecture documentation and presentation deck. | A new reviewer can set up and run the project from documentation; architecture matches implementation; slide story fits 15-20 minutes; live demo and backup evidence are ready. | README.md, docs/ARCHITECTURE.md and diagrams, role-authored sections, docs/DEMO_GUIDE.md, demo script/screenshots/curl examples and presentation source/output.
Phase 7 | Final QA, Rehearsal and Submission Freeze | 17-Aug to 18-Aug | Run the project from a clean state, validate final holdout metrics and artifact checksums, audit rubric/contributions, rehearse timed handoffs and verify failure fallback. | A: clean end-to-end data/pipeline run evidence. B: final holdout metrics and artifact checksum. C: clean Compose smoke test and backup demo verification. D: submission/rubric audit and timed technical rehearsal. | Clean clone/run succeeds; final metrics and checksums are frozen; documentation/commits cover the rubric; timed rehearsal and failure fallback pass; no unreviewed changes remain. | Final QA reports/checklists, frozen version tag or release candidate, updated PR/commit evidence, rehearsal log and submission checklist.

## Task Details
TASK DETAILS — STEPS, ACCEPTANCE, EVIDENCE AND HANDOFFS
Task ID | Objective | Detailed Steps | Output Path / Artifact | Acceptance Criteria | Reviewer | Evidence Required | Out of Scope | Branch / Work Area | Handoff / Coordination
PM-01 | Establish a safe, shared repository foundation. | 1. Create main, develop and agreed feature branches. 2. Commit base folders, .gitignore and repository conventions. 3. Invite collaborators and verify clone/push access. 4. Protect raw data, secrets, environments and large artifacts from Git. | Repository root, .gitignore, remote branches and collaborator access | - Required branches exist remotely - Base structure and .gitignore are committed - All four members can clone and push to assigned branches - No raw data, secrets, .env, .venv or large model artifacts are tracked | Member A | Repository URL, branch list and commit/PR link | Application features, model training and production deployment | project foundation / develop
PM-02 | Create a single task-tracking source of truth. | 1. Create the board/workbook with task IDs and phases. 2. Assign one owner, reviewer, priority, dates and dependencies to every task. 3. Define Backlog, In Progress, Review, Done and Blocked. 4. Require PR/commit evidence before closure. | GitHub Project or synchronized tracker workbook | - Every task has a unique ID, owner and deadline - Dependencies and deliverables are present - Status workflow is documented - Evidence fields exist and no duplicate task IDs remain | Member A | Board/workbook link or screenshot | Executing the technical tasks themselves | no code branch; tracker/GitHub Project
DOC-01 | Define the business, prediction and evaluation boundary. | 1. Write the hospital use case and intended users. 2. Fix prediction time at or immediately before discharge. 3. Document target mapping, scope/out-of-scope and constraints. 4. Define business proxy, model and system success metrics. | docs/PROBLEM_DEFINITION.md | - Business context and users are explicit - Prediction point prevents future-data leakage - Target mapping is stated and marked for data-dictionary confirmation - Functional/non-functional requirements and success metrics are included - The system is documented as decision support, not autonomous treatment | Members A, B and C | PR/commit link and review comments | Claiming real clinical impact before deployment | feature/responsible-ai
DATA-01 | Acquire and version the source dataset reproducibly. | 1. Download the approved Diabetes 130-US Hospitals files. 2. Record source, date, filename, size, rows/columns and checksum. 3. Store raw files as immutable local inputs. 4. Commit metadata but not patient-level raw files. | data/metadata/dataset_metadata.json and local data/raw files | - Files open successfully and checksum is recorded - Source/version metadata is complete - Raw files are immutable and ignored by Git - No patient-level raw data is committed | Member B | Metadata file and checksum command/output | Cleaning, imputation and model training | feature/data-pipeline
DATA-02 | Profile the dataset and identify initial quality risks. | 1. Inspect shape, columns, types and unique values. 2. Measure missing tokens/rates, duplicates and categorical cardinality. 3. Report original readmission classes and binary class balance. 4. Summarize outliers and subgroup availability. | notebooks/01_data_understanding.ipynb and reports/initial_eda.md | - Schema table is complete - Missing values including special tokens are counted - Duplicate count and target distribution are reported - Notebook/report is reproducible and does not modify raw data | Member B | Notebook/report PR and rendered tables/plots | Final preprocessing choices and model conclusions | feature/data-pipeline
DATA-03 | Lock the target and leakage exclusion policy. | 1. Map <30 to 1 and >30/NO to 0 after checking the dataset dictionary. 2. Document prediction time and feature availability. 3. List target, identifiers and future-derived fields that must be excluded. 4. Define patient/encounter split constraints. | docs/TARGET_AND_LEAKAGE.md | - Target mapping is verified against actual values - Prediction point is explicit - Each excluded field has a reason - Target and future information cannot enter features - Members B and C approve training/API implications | Members B and C | PR link and leakage checklist | Feature engineering and final schema validation | feature/data-pipeline
ML-01 | Define how experiments and models will be judged and tracked. | 1. Choose primary, secondary, calibration and capacity-based metrics. 2. Define train/validation/test usage and prohibit test-set tuning. 3. Set MLflow experiment/run naming, tags, parameters, metrics and artifacts. 4. Document dataset, split and feature version tags. | docs/ML_EVALUATION_SPEC.md and configs/mlflow.yaml | - A primary selection metric is named - Calibration and operational metrics are defined - MLflow convention is reproducible - Required versions/tags/artifacts are listed - No threshold or tuning decision uses the test set | Member C | PR link and specification review | Training final candidate models | feature/model-training
API-01 | Provide a runnable mock service for early integration. | 1. Create FastAPI app, configuration and API package. 2. Implement GET /health, GET /ready and POST /api/v1/predict. 3. Return an explicit mock response. 4. Add Swagger, Ruff and integration tests. | src/api, src/config, tests/integration/test_api.py | - Application imports and starts - /docs and /openapi.json load - /health returns 200 - /ready reports mock/not-loaded state - /api/v1/predict returns is_mock=true - Invalid request returns 422 - Ruff and pytest pass | Member D | PR/commit, test output and Swagger screenshot | Real model loading, predict_proba, final threshold and SHAP | feature/api
DATA-04 | Create a reusable raw-to-interim ingestion command. | 1. Validate input path and encoding. 2. Read CSV without mutating the raw file. 3. Normalize column names and calculate checksum. 4. Write metadata and an interim output atomically. 5. Log only aggregate row/column information. | src/data/ingestion.py and data/metadata/ingestion_manifest.json | - python -m src.data.ingestion runs successfully - Same input produces the same checksum/version metadata - Missing/invalid files fail clearly - Raw data is not overwritten - Interim output is created atomically | Member B | Command log, manifest and PR | Full schema validation, splitting and preprocessing | feature/data-pipeline
DATA-05 | Reject invalid data before downstream processing. | 1. Define required columns, types, categories and configurable quality thresholds. 2. Implement Pandera or equivalent validation. 3. Generate a versioned quality report. 4. Stop safely on failure and preserve the last valid processed dataset. 5. Create/update the data dictionary. | src/data/validation.py, configs/data_quality.yaml, reports/validation_report.json, docs/DATA_DICTIONARY.md | - Required columns/types/labels are checked - Negative and out-of-range values are detected - Missing and duplicate rules are configuration-backed - Failure stops the pipeline and does not overwrite prior valid output - Report contains schema status, missing rates, duplicates and positive rate | Member B | Passing/failing validation samples, report and PR | Comprehensive CI test execution, which is completed in Phase 5 | feature/data-pipeline
DATA-06 | Create reproducible leakage-safe train/validation/test partitions. | 1. Apply approved target and exclusions. 2. Choose and document patient-aware or encounter-aware split strategy. 3. Use fixed random seed and preserve class distribution. 4. Save IDs/hashes and summary statistics in a manifest. | src/data/splitting.py and data/splits/split_manifest.json | - Splits do not overlap - The same patient does not cross splits when patient-aware splitting is used - Target is absent from feature columns - Seed and ratios are recorded - Repeated execution reproduces the manifest | Member B | Split manifest, overlap test and PR | Hyperparameter tuning and final holdout evaluation | feature/data-pipeline
DATA-07 | Build one serializable preprocessing pipeline shared by training and serving. | 1. Define numeric and categorical columns from the validated schema. 2. Add train-only imputation and encoding. 3. Handle unseen categories safely. 4. Persist feature order/version and serialization behavior. 5. Test fit/transform/reload consistency. | src/features/preprocessing.py and preprocessor metadata/artifact reference | - Preprocessor fits only on training data - Validation/test use transform only - Unknown categories do not crash inference - Feature order/version is recorded - Serialized and reloaded preprocessor gives equivalent output | Member B | Unit tests, artifact checksum/reference and PR | Advanced feature engineering and model selection | feature/data-pipeline
ML-02 | Establish a no-skill reference level. | 1. Train DummyClassifier on the approved train split. 2. Evaluate on validation data with the agreed metrics. 3. Log strategy, versions, metrics and artifacts to MLflow. | src/models/train_dummy.py and MLflow run | - Run uses the versioned split - Strategy and random seed are logged - Primary/secondary metrics are stored - No test-set decision is made | Member C | MLflow run URL/ID and PR | Deployment or candidate-model selection | feature/model-training
ML-03 | Create the interpretable Logistic Regression baseline. | 1. Load the shared preprocessor and versioned split. 2. Train unweighted Logistic Regression. 3. Evaluate consistently and log parameters, metrics, plots and artifact references. | src/models/train_logistic.py, configs/models/logistic.yaml and MLflow run | - Shared DATA-07 preprocessor is used - Run is reproducible from config - Metrics and confusion matrix are logged - Model and preprocessing versions are traceable | Member C | MLflow run, config and PR | Class balancing, XGBoost and final threshold | feature/model-training
ML-04 | Measure the effect of class weighting fairly. | 1. Train class-balanced Logistic Regression using the same split/preprocessor. 2. Compare against ML-03 with identical evaluation. 3. Document precision-recall trade-offs and recommendation. | reports/logistic_imbalance_comparison.md and MLflow run | - Only class weighting changes between comparison runs - AUPRC, precision, recall and F1 are compared - Trade-off is explained - Test set remains untouched | Member C | Comparison table, MLflow run and PR | Final model selection and threshold optimization | feature/model-training
API-02 | Freeze a stable, data-aligned API contract. | 1. Define PredictionRequest, PredictionResponse and ErrorResponse. 2. Add types, required/optional rules, bounds, enums and descriptions. 3. Exclude target, identifiers and leakage fields. 4. Add valid request/response examples and schema tests. 5. Reconcile final field rules with DATA-05. | src/api/schemas.py, tests/unit/test_schemas.py, docs/api/API_CONTRACT.md | - Fields match approved target/leakage policy - Types and constraints are explicit - Swagger examples render - Target/leakage fields are absent - Members A and B approve input/output expectations - Schema tests pass | Members A and B | PR, schema tests and Swagger screenshot | Real model prediction, final threshold and explanations | feature/api | Draft can start after DATA-03; final validation uses DATA-05/DATA-07.
API-03 | Return consistent and privacy-safe client errors. | 1. Implement validation exception handler for 422. 2. Implement safe internal/server-unavailable handling. 3. Standardize error response schema. 4. Test missing fields, wrong types, invalid enums/ranges and forced internal errors. 5. Prevent stack traces and patient payloads from reaching clients/logs. | src/api/exception_handlers.py and tests/integration/test_api_errors.py | - Invalid inputs return structured 422 responses - Internal failures return safe 500/503 responses - No stack trace or patient payload is exposed - Swagger documents error responses - All error-path tests pass | Member D | PR and pytest output | Authentication, rate limiting and production observability | feature/api
API-04 | Package the FastAPI service as a reproducible image. | 1. Create Python 3.11 Dockerfile and .dockerignore. 2. Install pinned runtime dependencies. 3. Run Uvicorn on 0.0.0.0. 4. Add container health check behavior and verify /health. 5. Exclude raw data, secrets and local environments. | Dockerfile and .dockerignore | - docker build succeeds - Container starts and /health returns 200 - /docs is reachable - Runtime uses Python 3.11 - .env, .venv and data/raw are excluded from the image | Member D | Build log, image tag and curl output | Docker Compose orchestration and MLflow service | feature/api
OPS-01 | Orchestrate the API service locally with Docker Compose. | 1. Create docker-compose.yml with API service. 2. Configure build context, port mapping, environment and health check. 3. Add network/restart conventions for later services. 4. Verify clean start and stop. | docker-compose.yml and .env.example | - docker compose config passes - docker compose up --build starts a healthy API - /health and /docs work from host - No secret is hardcoded - docker compose down stops cleanly | Member C | Compose config/output, health screenshot and PR | MLflow persistence, Prometheus and Grafana | feature/monitoring
OPS-02 | Provide persistent local MLflow tracking. | 1. Add MLflow service to Compose. 2. Configure tracking URI, backend/artifact storage and persistent volume. 3. Verify UI access and restart persistence. 4. Document how training jobs connect. | docker-compose.yml, volume definitions and docs/MLFLOW_SETUP.md | - MLflow UI is reachable - Runs persist after container restart - Training can log to the configured tracking URI - mlruns and credentials are not committed | Member A | MLflow screenshot, persistence test and PR | Cloud artifact store and production registry | feature/monitoring
DATA-08 | Version the complete leakage-safe feature set V1. | 1. Select validated raw features allowed at prediction time. 2. Classify numeric/categorical fields and fix feature order. 3. Record excluded fields and rationale. 4. Publish a machine-readable manifest. | configs/features/feature_set_v1.yaml and docs/features/FEATURE_SET_V1.md | - Manifest has version, ordered features and types - Target/identifiers/leakage are absent - Preprocessor can consume the manifest - Missing or extra fields are testable | Member B | Manifest, unit test and PR | Feature selection based on final SHAP/fairness results | feature/data-pipeline
DATA-09 | Create a smaller deployment-oriented feature set V2. | 1. Identify removable high-cardinality, weak, unavailable or risky features. 2. Document keep/remove rationale. 3. Create a separate ordered manifest compatible with the same split strategy. | configs/features/feature_set_v2.yaml and docs/features/FEATURE_SET_V2.md | - V2 purpose and reduction rationale are explicit - V2 remains leakage-safe and prediction-time available - Manifest is versioned and loadable - Members B and C understand API/model implications | Members B and C | Manifest/rationale PR | Declaring V2 superior before controlled ablation | feature/data-pipeline
DATA-10 | Prepare controlled V1-versus-V2 ablation inputs. | 1. Use identical split manifest and evaluation protocol. 2. Build/serialize matching preprocessing outputs or references. 3. Record transformed feature counts and checksums. 4. Provide reproducible commands to Member B. | reports/feature_ablation_inputs.md and versioned feature/preprocessor references | - Only the feature set changes in the comparison - Same split and random seed are used - No train/validation/test leakage occurs - Inputs can be reproduced from committed code/configs | Member B | Checksums, commands and PR | Selecting the winning model, which belongs to ML-08 | feature/data-pipeline
ML-05 | Establish the default XGBoost benchmark. | 1. Train XGBoost with a documented baseline configuration on V1. 2. Evaluate with the same protocol as Logistic Regression. 3. Log parameters, metrics, plots and version tags. | src/models/train_xgboost.py, configs/models/xgboost_default.yaml and MLflow run | - Run uses V1 and approved split - Configuration and seed are logged - Metrics are comparable to baselines - Artifact/version traceability is complete | Member C | MLflow run, config and PR | Hyperparameter optimization and final selection | feature/model-training
ML-06 | Measure XGBoost class-imbalance strategies. | 1. Calculate a justified baseline scale_pos_weight. 2. Run unweighted and weighted comparisons under identical conditions. 3. Document precision-recall and calibration effects. | reports/xgboost_imbalance_comparison.md and MLflow runs | - Weight values and rationale are recorded - Runs share split/features/evaluation - AUPRC, recall, precision and F1 are compared - Recommendation is documented without using test data | Member C | MLflow comparison and report PR | Optuna search and final threshold | feature/model-training
ML-07 | Optimize XGBoost reproducibly with Optuna. | 1. Define bounded search space and primary objective. 2. Run 20-40 trials with fixed seed and approved validation/CV strategy. 3. Log trial history, best parameters and timing. 4. Do not tune on the final test set. | src/models/tune_xgboost.py, configs/models/xgboost_optuna.yaml and reports/optuna_results.md | - Search space and objective are documented - Requested trials complete or justified early stop is recorded - Best parameters/results are reproducible - Test set is untouched - Optuna and MLflow records are linked | Member C | Study database/summary, MLflow runs and PR | Calibration, threshold and final holdout scoring | feature/model-training
ML-08 | Select and export a deployable candidate bundle. | 1. Compare baselines, V1/V2 ablation and tuned XGBoost. 2. Select candidate using the Phase 1 metric policy and deployment constraints. 3. Export model, preprocessor, feature manifest and metadata. 4. Add versions, checksums and sample input/output. 5. Verify reload equivalence and hand off to Member C. | MLflow model bundle plus docs/MODEL_HANDOFF.md and metadata.json | - Selection rationale is documented - Model/preprocessor/manifest reload successfully - Checksums and versions are recorded - Reloaded predictions match original output - Sample request/expected probability is provided to Backend | Member C | MLflow artifact URI, checksums, handoff doc and PR | Final calibration, production threshold and per-request SHAP | feature/model-training
API-05 | Load the production model bundle once per application lifecycle. | 1. Define model bundle settings and artifact paths. 2. Load model, preprocessor, feature manifest and metadata during startup. 3. Validate compatibility and checksums. 4. Expose accurate readiness state. 5. Handle missing/corrupt artifacts without silent mock fallback. | src/api/lifecycle.py, src/api/dependencies.py and tests/unit/test_model_loading.py | - Artifacts load once at startup - Version mismatch/corruption is detected - /ready is false when loading fails and true when complete - Production mode never silently falls back to mock - Lifecycle tests pass with valid and invalid bundles | Member D | PR, startup logs without secrets and test output | Prediction transformation and final response logic | feature/api | Scaffold with a test bundle; cannot be Done until ML-08 handoff is validated.
API-06 | Serve real end-to-end readmission probabilities. | 1. Map validated request fields into the ordered model input. 2. Apply the exported preprocessor. 3. Call predict_proba on the loaded model. 4. Return real probability, model/feature versions and is_mock=false. 5. Compare API output against offline reference. | src/api/prediction_service.py, updated routes/schemas and tests/integration/test_real_prediction_api.py | - Feature order is enforced - Real preprocessor and predict_proba are used - Probability is within [0,1] - Response includes correct versions and is_mock=false - API and offline probability match within tolerance - Failures return safe 500/503 | Member D | End-to-end test, curl response and PR | Final calibrated threshold, risk bands and top factors | feature/api
OPS-03 | Expose privacy-safe Prometheus metrics for API/model health. | 1. Instrument request count, latency and status. 2. Expose prediction count/error and model-loaded gauge. 3. Use histograms for probability distribution where available. 4. Configure Prometheus scrape. 5. Avoid patient IDs and high-cardinality labels. | src/api/metrics.py and monitoring/prometheus/prometheus.yml | - /metrics is reachable - Counters/histograms/gauges update correctly - Prometheus target is UP - No patient identifier or unbounded label exists - Metrics integration tests pass | Member C | Metrics samples, Prometheus target screenshot and PR | Alert rules and advanced drift monitoring | feature/monitoring | Basic HTTP metrics can start earlier; prediction metrics are finalized after API-06.
OPS-04 | Create the first operational Grafana dashboard. | 1. Provision Prometheus as a datasource. 2. Create panels for requests, latency, 4xx/5xx, prediction errors and model status. 3. Add risk/probability distribution after real prediction metrics exist. 4. Persist and export dashboard JSON. | monitoring/grafana/provisioning and monitoring/grafana/dashboards/api-overview.json | - Grafana connects to Prometheus - Required panels display live data - Dashboard survives restart/provisions automatically - Risk/probability view uses aggregated metrics only - Evidence screenshot is captured | Member C | Dashboard JSON, screenshot and PR | Multiple advanced dashboards and cloud observability | feature/monitoring
ML-09 | Evaluate whether sigmoid calibration improves probability quality. | 1. Fit calibration only using training/validation-approved data. 2. Compare uncalibrated and sigmoid outputs. 3. Report Brier score and calibration curves. 4. Select or reject calibration with rationale. | src/models/calibration.py and reports/calibration_report.md | - No test leakage occurs - Brier score and calibration curve are produced - Comparison uses the same candidate model/split - Selected calibration method and version are documented | Member C | Report, plots, MLflow run and PR | Threshold selection and final holdout claims | feature/model-training
ML-10 | Select an operating threshold from validation data. | 1. Define capacity/business constraint and candidate thresholds. 2. Calculate recall, precision, specificity, F1 and workload trade-offs. 3. Choose and version the threshold. 4. Keep the final test set untouched until QA. | src/models/threshold_selection.py and reports/threshold_report.md | - Threshold comes only from validation data - Trade-off table and rationale are explicit - Capacity-based metric is reported - Threshold/version is exportable to the API bundle | Member C | Threshold report, config/metadata update and PR | Changing model hyperparameters using test-set results | feature/model-training
DATA-11 | Assess performance across available demographic/clinical subgroups. | 1. Define allowed subgroup slices from documented fields. 2. Calculate group sample sizes and agreed metrics. 3. Flag unreliable small groups and privacy concerns. 4. Summarize disparities without causal claims. | src/evaluation/fairness.py and reports/fairness_metrics.md | - Groups and denominators are documented - Metrics use the fixed candidate model/threshold - Small-sample limitations are flagged - No patient-level data is published - Findings feed Responsible AI documentation | Members B and D | Fairness table/report and PR | Claiming clinical fairness certification | feature/responsible-ai
ML-11 | Generate global SHAP evidence for model behavior. | 1. Use a reproducible representative evaluation sample. 2. Generate global summary and top-feature plots. 3. Document interpretation limits for correlated/encoded features. 4. Export a safe mapping usable by Backend if needed. | src/models/explainability.py and reports/shap_summary.md | - SHAP computation is reproducible - Global plot/top features are saved - No patient-level sensitive examples are exposed - Limitations and transformed-feature mapping are documented | Members C and D | SHAP artifacts/report and PR | Unbounded per-request SHAP latency or causal interpretation | feature/model-training
API-07 | Expose calibrated probability, risk band and approved top factors. | 1. Load versioned calibration/threshold metadata. 2. Map probability to documented low/medium/high bands. 3. Return safe top-factor representation based on the approved explainability design. 4. Update schema, Swagger and tests. | updated src/api schemas/routes/prediction service and tests | - Probability uses the selected calibration/version - Risk band follows documented thresholds - Top factors contain no raw patient identifiers - Response versions are traceable - Tests cover band boundaries and explanation shape | Member D | Swagger/curl examples, boundary tests and PR | Treatment recommendations and unrestricted local SHAP computation | feature/api
DOC-02 | Document responsible use, limitations and model facts. | 1. Describe intended users/use and out-of-scope use. 2. Record data/model versions, metrics and threshold. 3. Summarize fairness, privacy, explainability and operational risks. 4. List mitigations, monitoring and human-oversight requirements. | docs/RESPONSIBLE_AI.md and docs/MODEL_CARD.md | - Documents match actual artifacts/metrics - Clinical decision-support limitation is explicit - Fairness/privacy limitations are transparent - Monitoring and human review requirements are included - Members A, B and C review their sections | Members A, B and C | PR and cross-role review comments | Regulatory certification or unsupported clinical claims | feature/responsible-ai
TEST-01 | Automate data quality, leakage and preprocessing guarantees. | 1. Write tests for required schema, invalid values, missing thresholds and duplicates. 2. Test target/leakage exclusion and split overlap. 3. Test preprocessor serialization and unknown categories. 4. Provide small synthetic fixtures only. | tests/data and test fixtures | - Positive and negative validation cases pass - Leakage and split-overlap failures are detected - Preprocessing round-trip is tested - Tests use no raw patient dataset - Suite runs non-interactively in CI | Member B | pytest output, coverage and PR | Manual notebook-only checks | feature/data-pipeline
TEST-02 | Automate model artifact and prediction quality checks. | 1. Test artifact loading, feature compatibility and probability bounds. 2. Test deterministic predictions on fixed fixtures. 3. Verify minimum performance/calibration assertions with justified tolerances. 4. Test threshold metadata. | tests/models | - Model bundle reload test passes - Predictions are finite and within bounds - Version/feature mismatches fail clearly - Metric checks use stable fixtures/tolerances - Suite runs in CI | Member C | pytest output, coverage and PR | Re-tuning the model inside tests | feature/model-training
TEST-03 | Verify API behavior across valid, invalid and unavailable states. | 1. Test health/readiness and real prediction. 2. Test 422, 500 and model-unavailable 503 paths. 3. Test schema/version fields, risk bands and privacy-safe errors. 4. Run against app test client and container smoke path. | tests/integration | - Valid prediction succeeds - Invalid inputs return structured 422 - Unavailable/corrupt model returns safe status - Readiness matches lifecycle state - No stack trace or patient payload is exposed | Member D | pytest output, coverage and PR | Load/performance testing at production scale | feature/api
API-08 | Complete the public OpenAPI contract and examples. | 1. Add descriptions and representative examples for success/errors. 2. Document health/readiness semantics. 3. Document model/threshold/version fields. 4. Export or snapshot OpenAPI if the team chooses to version it. | src/api schema metadata and docs/api/openapi.json (optional generated artifact) | - /docs covers all endpoints and error responses - Examples match actual tests - Required/optional fields are clear - No sensitive real patient example is included | Member D | Swagger screenshot, OpenAPI diff and PR | Frontend implementation and external public hosting | feature/api
OPS-05 | Harden Compose with service health and persistent state. | 1. Add health checks and dependency conditions for API, MLflow, Prometheus and Grafana. 2. Define persistent volumes and startup order. 3. Verify restart behavior and one-command clean start. 4. Document reset/cleanup commands. | docker-compose.yml, volume/health configuration and docs | - All services become healthy from one command - Persistent MLflow/Grafana state survives restart - API waits for required dependencies - Clean stop/reset procedure is documented | Member C | Compose ps output, restart evidence and PR | Cloud orchestration and autoscaling | feature/monitoring
OPS-06 | Run quality gates automatically on GitHub. | 1. Create workflow for dependency install, Ruff, pytest and coverage. 2. Run data/model/API suites. 3. Build the API image. 4. Use cache and safe non-secret test configuration. 5. Require the workflow on PRs. | .github/workflows/ci.yml | - Workflow triggers on pull requests/pushes as agreed - Lint and all test suites pass - Coverage is reported - Docker build succeeds - No secret or raw data is required | Member A | Green GitHub Actions run and PR | Automated cloud deployment | feature/monitoring
OPS-07 | Alert on meaningful availability and performance failures. | 1. Define latency, error-rate and model-unavailable alerts. 2. Use justified windows/thresholds. 3. Validate Prometheus rule syntax. 4. Document severity and response action. | monitoring/prometheus/alerts.yml and docs/MONITORING.md | - Rules load without errors - Alerts cover latency, error and model availability - Threshold rationale is documented - No patient-level labels are used | Member C | promtool/rule validation output and PR | Pager integration and advanced drift alerts | feature/monitoring
DOC-03 | Make the repository reproducible for a new reader. | 1. Document prerequisites and local setup. 2. Document ingestion/training/API/Compose commands. 3. Add troubleshooting and repository structure. 4. Link model, Responsible AI and monitoring documents. | README.md | - Clean setup instructions are executable - Commands match current code and ports - Dataset/artifact policies are clear - Troubleshooting covers common failures - All major documents are linked | Member A | README PR and clean-reader review | Replacing detailed architecture/model documents with one oversized README | feature/responsible-ai
DOC-04 | Describe the implemented architecture and data/model flow. | 1. Document components and role ownership. 2. Draw raw-to-model-to-API-to-monitoring flow. 3. Document artifact/version handoffs and failure states. 4. Ensure diagrams match actual repository/services. | docs/ARCHITECTURE.md and docs/architecture-diagram.png | - Diagram and prose match implementation - Data/model/API/monitoring handoffs are shown - Dependencies and failure behavior are explained - All four roles review their components | Members A, B and C | Architecture PR and diagram review | Future cloud architecture not implemented in the project | feature/responsible-ai
DOC-05 | Build a coherent 15-20 minute project presentation. | 1. Create story: problem, data, method, system, results, risks and demo. 2. Use evidence from final reports/artifacts. 3. Assign speaking ownership and timing. 4. Prepare concise backup slides. | presentation deck and source assets | - Deck fits 15-20 minutes - Claims match final evidence - All roles have clear speaking sections - Architecture/results/Responsible AI/demo are covered | All members | Deck file, rehearsal timing and review notes | New technical features after system freeze | feature/responsible-ai
DATA-12 | Provide the final data, target and leakage narrative. | 1. Summarize dataset version/profile. 2. Explain target mapping, leakage policy, split and preprocessing. 3. Report feature-set and data-quality decisions. 4. Provide figures/tables for README/slides. | docs/sections/DATA_AND_LEAKAGE.md | - Text matches final pipeline/configs - Leakage safeguards are explicit - Data limitations are transparent - Figures/tables are reproducible and privacy-safe | Member B | Section PR and source figure links | Model tuning and API implementation details | feature/data-pipeline
ML-12 | Provide the final model and evaluation narrative. | 1. Summarize baselines, XGBoost, Optuna and ablation. 2. Explain calibration and threshold selection. 3. Report final validation/holdout metrics with limitations. 4. Provide figures/tables for README/slides. | docs/sections/MODEL_RESULTS.md | - Metrics match frozen MLflow/report values - Validation versus test usage is clear - Threshold/calibration rationale is included - No unsupported superiority claim is made | Member C | Section PR and MLflow/report references | Data ingestion and API operations | feature/model-training
API-09 | Document API, Docker and demo execution. | 1. Document native and container startup. 2. Provide curl examples for health, readiness, valid and invalid prediction. 3. Explain model artifact configuration and common errors. 4. Document demo reset and offline fallback. | docs/DEMO_GUIDE.md | - Commands work from a clean environment - Examples match final OpenAPI schema - Docker/Compose steps are accurate - Failure recovery and fallback are documented | Member D | Guide PR and clean-run evidence | Cloud deployment instructions not implemented | feature/api
DEMO-01 | Prepare a reliable live demo and backup evidence. | 1. Write a timed demo script. 2. Prepare valid, invalid and unavailable-model scenarios. 3. Capture screenshots/curl output and optional recording. 4. Verify no sensitive data appears. | docs/DEMO_SCRIPT.md and docs/demo_evidence | - Live flow can be completed within allocated time - Backup evidence covers every critical step - Failure scenario is understandable - Examples use synthetic/non-sensitive data | Member D | Script, screenshots and rehearsal notes | New feature development | feature/api
QA-01 | Prove the full pipeline is reproducible from a clean state. | 1. Use a clean environment/clone. 2. Run ingestion, validation, split, preprocessing and required training/evaluation commands. 3. Run the full test suite. 4. Record versions, commands, timings and outcomes. | reports/qa/clean_end_to_end_run.md | - Clean run completes without hidden local state - All required tests pass - Versions/checksums are recorded - Any approved manual step is documented | Member B | Clean-run log and checklist | Changing frozen model/features unless fixing a critical defect | release candidate / develop
QA-02 | Freeze and verify final holdout results and artifacts. | 1. Evaluate the frozen candidate once on the final holdout. 2. Record final metrics and uncertainty/limitations. 3. Verify model/preprocessor/metadata checksums. 4. Update final reports without retuning. | reports/qa/final_holdout_metrics.md and artifact checksums | - Holdout is evaluated only after decisions are frozen - Metrics match saved predictions/artifacts - Checksums verify the submitted bundle - No post-hoc retuning occurs | Member C | Final metric table, MLflow run and checksum output | Further optimization after seeing holdout results | release candidate / feature/model-training
QA-03 | Verify the packaged system starts and serves correctly. | 1. Build from a clean checkout. 2. Start all services with Docker Compose. 3. Check health/readiness/metrics/Grafana/MLflow. 4. Run valid and invalid prediction smoke tests. 5. Stop and restart to verify persistence. | reports/qa/compose_smoke_test.md | - All services become healthy - Endpoints and dashboards are reachable - Real prediction and errors behave correctly - Persistent services survive restart - No local-only dependency is required | Member D | Compose ps, curl outputs and screenshots | Cloud load testing | release candidate / feature/api
QA-04 | Audit submission completeness and contribution evidence. | 1. Map rubric items to repository evidence. 2. Check task statuses, PRs, commits and reviewers. 3. Verify docs, artifacts and presentation links. 4. Confirm no secrets/raw data/unapproved binaries are tracked. | docs/SUBMISSION_CHECKLIST.md | - Every rubric item has evidence or an explicit limitation - Each member has traceable contributions - All files/links open - Repository security/data policy checks pass | All members | Completed checklist and audit notes | Adding unreviewed features during freeze | release candidate / feature/responsible-ai
DEMO-02 | Rehearse the complete technical presentation with timed handoffs. | 1. Run the full slide and demo sequence. 2. Time each speaker and transition. 3. Record questions, weak explanations and corrective actions. 4. Repeat until within the limit. | docs/REHEARSAL_LOG.md | - Full run fits the time limit - Speaker handoffs are explicit - Critical Q&A ownership is practiced - Actions are resolved before submission | All members | Rehearsal log and timing | Changing core implementation without critical reason | no code branch; team rehearsal
DEMO-03 | Verify failure-mode and offline backup demonstration. | 1. Simulate unavailable model/service or network-independent fallback. 2. Run backup screenshots/recording/curl evidence. 3. Confirm presenters can explain the failure and recovery. 4. Store assets locally and in the submission package. | docs/BACKUP_DEMO_CHECKLIST.md and backup assets | - Offline backup opens without external dependency - Failure scenario and recovery are demonstrated - Assets match the final system - No sensitive data is included | Member D | Completed checklist and backup asset test | New features or redesign | feature/api / local submission package

## Lists (hidden)
Backlog | Critical | Member A - Data | Phase 1
In Progress | High | Member B - ML | Phase 2
Review | Medium | Member C - Backend | Phase 3
Done | Low | Member D - MLOps/Docs | Phase 4
Blocked |  |  | Phase 5
Phase 6
Phase 7